## Sheet1
,
Sprint Backlog
| User Stories | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Members | Acceptance Criteria
| As a user I should be able to get myselft registered in the web app | Design data model to store user data | 14 | 21 | 13 | 8 | 5 | 3 | Sunday (HOLIDAY) | 2 | 1 | 0 | 0 | 0 | 0 | Sunday (HOLIDAY) | Haseeb, Wahaj | User should be able to signup and his/her data should be stored securely And the UI should be effective and efficent.
|  | Design Registration from UI | 12 | 8 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Usman
|  | Code to create a unique id for user | 25 | 27 | 19 | 17 | 13 | 8 |  | 8 | 5 | 3 | 2 | 1 | 0 |  | Haseeb, Wahaj
|  | Design database | 18 | 8 | 5 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Haseeb
|  | Connect user data to server | 11 | 8 | 5 | 5 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Wahaj
| As a user I should be able to view/order/reviews of the products | Provide product viewing option | 12 | 21 | 13 | 8 | 5 | 3 |  | 2 | 1 | 0 | 0 | 0 | 0 |  | Haseeb, Wahaj | After user created his/her profile, the users should be able to edit their profile and User should see the products and order them from their carts
|  | Design UI place order | 15 | 25 | 18 | 17 | 13 | 8 |  | 8 | 5 | 3 | 2 | 1 | 0 |  | Usman
|  | Connect server to program so user can see online reviews | 13 | 13 | 8 | 5 | 5 | 3 |  | 2 | 1 | 1 | 0 | 0 | 0 |  | Haseeb, Wahaj
| As an admin I should be able to access on add/remove/manage stocks/order details of the product | Provide profile edit option, and design its UI for all users | 18 | 21 | 13 | 8 | 5 | 3 |  | 2 | 1 | 0 | 0 | 0 | 0 |  | Usman, Haseeb | After user created his/her profile, the admin should be able add or remove the products and he/she can also see the order placed with details
|  | Design UI to add/remove products | 8 | 8 | 8 | 5 | 5 | 3 |  | 1 | 0 | 0 | 0 | 0 | 0 |  | Usman, Wahaj
|  | Design manage stock system | 25 | 25 | 18 | 17 | 13 | 8 |  | 8 | 5 | 3 | 2 | 1 | 0 |  | Haseeb
|  | Connect server to program so admin can see the order placed | 13 | 13 | 8 | 5 | 5 | 3 |  | 2 | 1 | 1 | 0 | 0 | 0 |  | Wahaj
Group Member 1 | Syed Fasih Ahmed | Scrum Master
Seat No. | (EP-1850114)
Group Member 2 | Wahaj Aslam | Developer 1
Seat No. | (EP-1850137)
Group Member 3 | Muhammad Haseeb | Developer 2 + Product Owner
Seat No. | (EP-1850068)
Group Member 4 | Syed Usman Naseem | UI/UX Designer
Seat No. | (EP-1850127)